## module list
Sr. | Module | Screen Number | Date of submit | Note | Payment Upwork | Direct Paymnet
1 | Login Register Profile Module | 1.0-1
| Order New Photo Frame / Order List | 2.0-8.2
| Order New Photo Album | 10.0-10.2 | 2017-04-24 | Design and Implemantation
| Code Review |  | 2017-04-25 | By Sandeep
| Unit Testing & Milestone Complete |  | 42851 | By Imtiyaz | 50 | 0
2 | Order Bulk Photo Print | 11.0-
| Call Executive | 12
| Order wall / custom wall | 13-14
| Notifications | 15 | 2017-05-01 | Design and Implemantation
| Code Review |  | 2017-05-02 | By Sandeep
| Unit Testing & Milestone Complete |  | 42858 | By Imtiyaz | 50 | 80
3 | Business Enrollment | 16
| Feed back | 17
| Cart | 18
| Hot Offers | 19 | 2017-05-08 | Design and Implemantation
| Code Review |  | 2017-05-09 | By Sandeep
| Unit Testing & Milestone Complete |  | 42865 | By Imtiyaz | 50 | 100
4 | Contacts /about us / Support / app settings | 20
| Obituary Wall | 21,22,23 | 2017-05-15 | Design and Implemantation & Design of 24,25,26
| Code Review |  | 2017-05-16 | By Sandeep
| Unit Testing & Milestone Complete |  | 2017-05-17 | By Imtiyaz | 50 | 100
5 | Sweet Memory | 24,25,26
| Event Module | 27-30
| App Notifications | 31,32 | 2017-05-22 | Design and Implemantation
Bug solving and minor changes
| Code Review |  | 2017-05-24 | By Sandeep
| Unit Testing & Milestone Complete |  | 2017-05-29 | By Imtiyaz | 50 | 150
| Live on Playstore |  | 2017-06-01 |  |  | 70
[5 empty] | 250 | 500 | 750

## Sheet1
Splash Screen | 1 Screen | Design Implementation and development | Query | Date of submission
Walk \Through Screen | 5 walk through Screens
User Management | Login/Sign Up Design & Implementation | Email with OTP verification
Mobile with OTP verification
Facebook
Gmail
Email with OTP verification
Mobile with OTP verification
Facebook
Gmail
| Profile Screen | User Profile Design Implementation and development |  | 24-04-2017
Home Page | Home Page | Design Implementation and development | Only design notification after module compelitation
| Notification | Screen Design implementation and development |  | 2017-05-11
Order Module | Order Frame Photos | Frame Bit Screen Design Implementation and Development
Pre-view Frame with Photo Screen design and Implementation and Development
Photo Crop screen Design and Implementation
Order Frame Photos form screen design implementation and development
Order summary preview screen design implementation and development
Order payment screen design implementation and development
Order Final payment successful screen design implementation and development
Order History screen design implementation and development
|  | Order cart screen design implementation and development |  | 2017-05-17
| Order Print Photos | Order Print Photos screen design implementation and development
Bulk image Gallery screen design implementation and development
Order summary preview screen design implementation and development
Order payment screen design implementation and development
Order Final payment successful screen design implementation and development
Order History screen design implementation and development
|  | Order cart screen design implementation and development |  | 2017-12-05
| Order Photo Album | Order Photo Album screen design implementation and development
Bulk image Gallery screen design implementation and development
Order summary preview screen design implementation and development
Order payment screen design implementation and development
Order Final payment successful screen design implementation and development
Order History screen design implementation and development
|  | Order cart screen design implementation and development |  | 2017-05-26
| Call Executive | Call executive form screen design implementation and development
Order payment screen design implementation and development
Order Final payment successful screen design implementation and development
|  | Order History screen design implementation and development |  | 2017-05-31
| Order Custom Wall | Order Custom Wall Form screen design implementation and development
Order payment screen design implementation and development
Order Final payment successful screen design implementation and development
Order History screen design implementation and development
|  | My Cart screen design implementation and development |  | 2017-06-08
| Order Purchase New Wall | Order Purchase new wall screen design implementation and development
Order payment screen design implementation and development
Order Final payment successful screen design implementation and development
Order History screen design implementation and development
My Cart screen design implementation and development
| Hot Offers | Hot Offers screen design implementation and development |  | 2017-06-15
Unit testing | by Jaydeep
Funtional integration Testing | by Imtiyaz |  | Payment
Side Menu | My Contacts | My Contact screen design implementation and development
Create Broadcast screen design implementation and development
| My Offers | My Offers screen design implementation and development
Cenotaph | Cenotaph Shared List view | Cenotaph list view screen design implementation and development
Cenotaph Detail View Screen Design implementation and development
Like screen design implementation and development
Comment screen design implementation and development
Tribute screen design implementation and development
Share screen design implementation and development
| Cenotaph Personal List view | screen design implementation and development
Cenotaph Detail View Screen Design implementation and development
Like screen design implementation and development
Comment screen design implementation and development
Share screen design implementation and development
| Cenotaph Template Screen | Cenotaph Template screen design implementation and development
| Cenotaph Create New Form | screen design implementation and development |  | 2017-06-25
Sweet Memories | Sweet Memories Shared List view | Sweet Memories list view screen design implementation and development
Sweet Memories Detail View Screen Design implementation and development
Like screen design implementation and development
Comment screen design implementation and development
Tribute screen design implementation and development
Share screen design implementation and development
| Sweet Memories Personal List view | screen design implementation and development
Sweet Memories Detail View Screen Design implementation and development
Like screen design implementation and development
Comment screen design implementation and development
Share screen design implementation and development
| Sweet Memories Template Screen | Sweet Memories Template screen design implementation and development
| Sweet Memories Create New Form | screen design implementation and development
Unit Testing | by jaydeep |  |  | 2017-07-05
Funtioanl integration testing | by Imtiyaz |  | Payment
Events | Shared Events List View | screen design implementation and development
| Personal Events List View | screen design implementation and development
| Event Detailed View | screen design implementation and development
| Create New Event | screen design implementation and development
Event accepted Screen design implementation and development
Event - denied Screen design implementation and development
Event - Maybe Screen design implementation and development
Event - Shared Screen design implementation and development
Business User Enrollment | Business User Enrollment | list and create new form screen design implementation and development
| Feedback | list and create new form screen design implementation and development |  | 2017-07-15
Unit Testing | by jaydeep
Funtioanl integration testing | by Imtiyaz |  | Payment
Side Menu | App notification setings | screen design implementation and development
Create new notification screen design implementation and development
| Help and Legal Support | screen design implementation and development
| About Us | screen design implementation and development
| My Orders | screen design implementation and development
| Manage Shipping Address | screen design implementation and development |  | 2017-07-20
Unit Testing | by jaydeep
Funtioanl integration testing | by Imtiyaz |  | Payment